## Path Worksheet
ETM Path Worksheet
Earned Value & Earned Time · Appendix C.3 · P6 Project Controls · © 2026 P6 Project Controls. All rights reserved.
Path name |  | A, wet finishes (steel workshop example)
Milestone duration from path start (working days) |  | 102
Actual time AT: working days from path start to data date |  | 70
Cost SPI for the same data date (optional, enter to test the 0.10 gap)
Element (task, lag or subnet) | Type | Planned (days) | % complete (tasks) | Elapsed days (lags) | Earned time (days) | Notes
SS lag, masonry to plastering | Lag | 15 |  | 15 | 15 | Lag earns elapsed days, capped at its length
Plastering | Task | 30 | 100% |  | 30
A1 Thermal and moisture protection | Task | 7 | 100% |  | 7
A2 Wall tiles | Task | 20 | 60% |  | 12
A3 Floor tiles | Task | 20 | 0% |  | 0
Doors and windows | Task | 10 | 0% |  | 0
Path total |  | 102 |  |  | 64
Result |  | Value | Formula
Planned duration PD (days) |  | 102 | Σ planned along the path
Earned time ET (days) |  | 64 | Σ earned along the path
SV(ETM) (days) |  | -6 | ET − AT
SPI(ETM) |  | 0.91429 | ET ÷ AT
Status band |  | Amber | Green ≥ 0.95 · Amber 0.85–0.95 · Red < 0.85
Forecast duration (days) |  | 111.5625 | AT + (PD − ET) ÷ SPI
Forecast float (days) |  | -9.5625 | Milestone − forecast duration
Float trigger |  | Below 10-day trigger: watch list | Trigger: forecast float under 10 working days
Cost SPI − SPI(ETM) |  |  | A gap above 0.10 means value is earned off this path
How to use
Edit only the yellow cells with blue text. Black cells are formulas.
List the path in logic order from its start to the milestone. Use baseline (planned) durations from P6, converted from hours to days.
Type = Task: earned time = planned × % complete. Type = Lag: earned time = elapsed working days, capped at the lag length.
Type = Subnet: for parallel branches, enter the longest earned branch in "Elapsed days" (the subnet rule, Chapter 13), and the branch's planned days in "Planned".
The example rows are path A of the steel workshop at working day 70 (Chapter 13): ET 64, SPI(ETM) 0.91, forecast 111.6 days, forecast float −9.6. Clear them before use.
Keep one copy per named path per update, and trend the results over at least three updates.