[CONTRACTOR LETTERHEAD]

[Date]

VIA [email / contract portal / certified mail]

[Name], Contracting Officer

[Agency / Contracting Office]

[Street address]

[City, State ZIP]

Subject:  Request for Equitable Adjustment No. [REA-00X]: [Short title of event]

Contract No. [Number]; Task Order / Modification [Number, if any]

Project: [Project title and location]

References: (a) [Notice letter ref. and date]; (b) [RFI / direction / change order ref. and date]; (c) [other key correspondence]

Dear [Mr./Ms. Last name]:

[Contractor legal name] (“the Contractor”) submits this Request for Equitable Adjustment (REA) for an adjustment to the contract price and time arising from [one-sentence description of the event]. The Contractor requests [X] calendar days of time extension and [$ total] in price adjustment, as summarised below and supported in the enclosed documentation.

1.  Background

[Two to four sentences: what happened, when it started, who directed or caused it, and which work was affected. Cite the references above.]

2.  Contractual Basis

The Contractor is entitled to an equitable adjustment under [clause(s), e.g. FAR 52.243-4 Changes; FAR 52.236-2 Differing Site Conditions; FAR 52.242-14 Suspension of Work] because [one-sentence entitlement statement]. Written notice was provided on [date] by reference (a), within the period required by [clause].

3.  Time Impact

A Time Impact Analysis (Enclosure 2) was performed using accepted schedule update [No. / data date], the last accepted update before the event. The unimpacted schedule forecasts completion on [date]; with the event fragnet inserted, forecast completion is [date]. The difference of [X] calendar days is the delay attributable to this event. The Contractor requests that the contract completion date be revised from [current date] to [revised date].

4.  Price Adjustment

The requested adjustment is summarised below and detailed in Enclosure 3:

| Direct costs of the changed work (labour, material, equipment, subcontract) | [$ amount] |
| --- | --- |
| Time-related field costs for [X] calendar days of extended performance | [$ amount] |
| Home-office overhead (method: [e.g. Eichleay / percentage markup]) | [$ amount] |
| Profit on changed work at [X]% | [$ amount] |
| Bond and insurance premium adjustment | [$ amount] |
| Total requested adjustment | [$ total] |

5.  Request

The Contractor requests a bilateral modification adjusting the contract price by [$ total] and the contract completion date to [revised date]. We propose a meeting within [14] days of receipt to review this REA and are available at the Government’s convenience. We would appreciate a response by [date].

This REA is submitted to resolve the matter by negotiation. The Contractor reserves its rights under the contract, including the right to submit a claim under the Disputes clause if agreement cannot be reached, and to update this request if the effects of the event continue beyond [date].

Please direct questions to [Name, title] at [phone] or [email].

Respectfully,

[Signature]

[Name]

[Title]

[Contractor legal name]

Enclosures:  1. Chronology and supporting correspondence   2. Time Impact Analysis with native schedule files   3. Cost proposal and backup   [4. REA certification, where required]

cc:  [Contracting Officer’s Representative]; [Contractor project manager]; [file]

How to Complete This Template

Guidance notes from Chapter 18. Delete this page before sending.

| Section | Guidance |
| --- | --- |
| Subject line | Number each REA and give it a short, neutral title. Use the same number on every related document. |
| References | List the notice, directions and RFIs that establish the event and notice compliance. Reviewers check these first. |
| Opening paragraph | State the time and money requested in the first paragraph. The reader should know the ask immediately. |
| Contractual basis | Name the clause and the notice date. Keep entitlement to one sentence here; the detail belongs in the enclosures. |
| Time impact | Quote the unimpacted and impacted dates from the TIA. Measure from the unimpacted forecast, never from the contract date (Chapter 14). |
| Price adjustment | Totals only in the letter; the cost proposal carries the build-up. Separate time-related costs from direct costs. |
| Request and tone | Ask for a bilateral modification and a meeting. Keep the tone factual and cooperative: an REA is a negotiation document. |
| REA or claim? | Do not ask for a Contracting Officer’s final decision unless you intend to submit a claim under the Contract Disputes Act. A written demand for a final decision can turn the document into a claim, with certification and other consequences (Chapter 18). |
| Certification | Certify only where required by the contract or agency supplement. A CDA claim above $100,000 needs the separate claim certification in FAR 33.207. |

Optional certification (only where required, e.g. DFARS 252.243-7002 for DoD contracts exceeding the simplified acquisition threshold):

“I certify that the request is made in good faith, and that the supporting data are accurate and complete to the best of my knowledge and belief.”   [Name, Title, Signature, Date]

This template is general guidance, not legal advice. Confirm clause numbers, notice periods and certification requirements against your contract and agency supplement.